## Slide 1
THE FIRST SERVICE INTO THE HORIZONTAL OPERATING MODEL
SQL Server Pod
Operating model · 90-day pilot
One engine, owned end-to-end, automating its own toil. Ninety days to build the pattern — not to transform an estate.
Zephyr On-Prem Program | Technology Infrastructure
Notes: Frame: the pilot is approved. This is how we run it — and the two things we need agreed today are the liaison names and the verdict criteria.

## Slide 2
PURPOSE
How we're going to run it
The pilot is approved and the pod is delivering from day one. This is how it operates — and how we'll know it's working, agreed before we start rather than after.
WHAT THIS IS
A pilot, not a rollout
A time-boxed test of the horizontal model on one engine
Contained blast radius — survivable if we're wrong
Real adjust and stop triggers, agreed up front
WHAT WE'LL DELIVER
Pattern, not transformation
Toil falls in ops, compliance and incidents
The horizontal contracts deliver without becoming gates
A pattern the next engine inherits
WHAT WE WON'T
Said plainly, up front
No estate-wide cost savings in 90 days
No headcount impact
No migrations, no other engines
THE DISTINCTION THAT GOVERNS EVERYTHING
Pod goals outlive the pilot. Pilot goals expire at day 90. The pod exists to reduce SQL Server toil — true on day 91 whatever the verdict. The pilot is a 90-day test of whether the horizontal model is the right way to do it. Conflating them is why 'unsuccessful' sounds existential.
WHAT WE NEED FROM THIS ROOM TODAY
1. Name the liaisons by day 15 — individuals, with backups 2. Back the pod lead's call on who burns toil 3. Agree the GO / ADJUST / STOP criteria — today, not at day 90
SQL Server Pod | Zephyr On-Prem Program

## Slide 3
POD MISSION
Why this pod exists
Reduce the toil of running SQL Server — in operations, compliance and incidents —
by owning the engine end-to-end and automating our own toil.
OPERATIONS TOIL
The toil
Provisioning · patching · config changes · access · restores
The mechanism
Golden modules · self-service · policy-as-code
COMPLIANCE TOIL
The toil
Evidence assembly · audit prep · drift · exceptions · attestation
The mechanism
Evidence automation · compliant by construction
INCIDENT TOIL
The toil
Alert triage · repeat incidents · known-error firefighting
The mechanism
Prevention agents · alert triage · SRE practice
AUTOMATION IS AN ACTIVITY, NOT A ROLE
There is no automation team and there are no automation engineers. Anyone with cycles automates — the pod lead decides who burns the toil.
The person who feels the toil is the person who eliminates it. That is why there is no seam: not between teams, and not inside the pod either. An automation team would rebuild the build/run seam one level down — same caste system, same failure: people who don't feel the pain automate the wrong things.
North star: toil % — the share of pod capacity spent on manual, repetitive, automatable, reactive work. One number. Everyone's number.
SQL Server Pod | Zephyr On-Prem Program
Notes: If challenged on 'anyone can automate' — the risk is diffusion (everyone's job = nobody's job). Mitigations: pod lead protects the time, board makes it visible as a work type, toil % measures it.

## Slide 4
POD GOALS · ENDURING
What the pod is for — true on day 91
These do not expire with the pilot. Whatever the day-90 verdict, the pod still has this job.
GOAL
MEASURE
OFF TRACK IF
G1
Cut operations toil
Ops toil % vs. baseline · provisioning lead time · self-service rate
Engineers still hand-building; module exists but nobody uses it
G2
Cut compliance toil
Evidence person-hours per audit cycle · auto-assembly %
Audit pack still assembled by hand the week before
G3
Cut incident toil
Alert-to-incident ratio · repeat-incident % · MTTR
Same incidents recurring; page volume unchanged
G4
Own the engine end-to-end
% work through the front door · build and run in one team
Work arrives via side channels; run drifts back out
THERE IS NO OWNER COLUMN HERE, AND THAT IS DELIBERATE
All four goals belong to the whole pod. Compliance toil is not "Tigers' goal" and ops toil is not "Eng's goal" — parcelling them out rebuilds the silos one level down and gives everyone a goal that isn't theirs to duck. Whoever has cycles works whichever pool needs it; the pod lead makes that call week to week.
Targets are relative deltas. Absolute numbers get filled at day 30 once the baseline lands — in public, once. A target invented on day 0 is a number nobody believed anyway.
SQL Server Pod | Zephyr On-Prem Program

## Slide 5
PILOT GOALS · EXPIRE AT DAY 90
What the 90 days delivers
P1
Make the contracts work
Consume Zephyr, IntOps and Capacity as products — rebuild nothing
Measure: Blocked-on-horizontal days · module reuse · Zephyr pull-ins/week
Off track if: Pod is gated waiting on horizontals — or quietly rebuilds what it should consume
P2
Put the agents to work
Agent-proposed change on patch and evidence, with a human deciding
Measure: PRs proposed / approved / rejected
Off track if: Agents propose noise (>40% reject) — or humans rubber-stamp (<5% reject)
P3
Produce the repeatable pattern
The artifact engine #2 inherits
Measure: The pattern doc: charter, contracts, board config, toil taxonomy, metrics
Off track if: SQL Server gets quieter but nothing transfers
NON-GOALS
What this pod is not chartered to do
✗
ENGINE migration — SQL Server to PostgreSQL. That's Home-of-Best-Fit, wave 2
✗
Version rationalization or re-platforming at scale
✗
Solving any other engine
✗
Estate-wide cost savings or headcount impact
✗
Owning the control plane, compliance framework or AIOps platform
✗
Org redesign or role changes
✓ ESTATE migration IS in scope. Moving existing instances onto the automated pattern is how the toil goals get realised — see next slide. Different thing entirely from engine migration.
P3 is the pilot's actual deliverable. A quieter SQL Server estate with no transferable pattern is a successful project and a failed pilot. Every non-goal above will be proposed by someone in this room — each one quietly kills the 90 days.
SQL Server Pod | Zephyr On-Prem Program

## Slide 6
THE POD
Who's in it — and who isn't
One test settles every case: does this function carry the SQL Server pager? Yes → in the pod. No → it's a contract.
CORE
Dedicated · carry the pager
Pod Lead — owns roadmap and outcome
Engineers — modules, automation, IaC
Ops — run, day-2, on-call
SQL SMEs — deep engine expertise
Dedicated SRE — raises prod issues as prioritized bugs
Intelligent Ops — builds the agents that predict, prevent and auto-remediate incidents
Tigers (Risk & Compliance) — evidence built in, not bolted on
PLACEHOLDER
Brought in at the right time
Architecture — early, on offering shape and HA/DR tier design
Zephyr Control Plane — when we publish modules and register the offering
Capacity Management — once the estate is instrumented and rightsizing starts
Named individual + named backup, so there is always someone to call
A seat at the table when their work is live — not a queue to join
Engaged by plan; available by SLA when something unplanned surfaces
CONSUMED AS PRODUCT
Contract + SLA · no seat
The control plane, portal and policy engine
The compliance framework and regulator interface
The AIOps platform and telemetry backplane
Rightsizing and forecasting agents
The pod consumes these — it does not rebuild them
PLACEHOLDER IS A PLAN, NOT A PARKING SPACE
These are people we bring in deliberately, at the point in the 90 days where their work actually lands — architecture early on design, Zephyr when we publish, Capacity once the estate is instrumented. Named individual and named backup, so there is always someone to call. The alternative — a name on a list we hope answers — is a ticket queue with better manners, which is exactly what this model claims to have eliminated. If we cannot name them by day 15, the horizontal model has already told us something.
SQL Server Pod | Zephyr On-Prem Program

## Slide 7
INTERACTION MECHANICS
SQL Server Pod ↔ Zephyr · CMP · Intelligent Ops
Three cross-cutting squads. Three two-way contracts. Each ships a product the pod consumes; the pod emits signals — and gaps — the cross-cutting squad turns into next-gen automation. No tickets, no gates.
ZEPHYR HYBRID CLOUD
Zephyr Control Plane
Substrate · APIs · UX · Policy
OWNS
Module registry & control plane
Self-service developer portal
Policy engine · lifecycle · evidence
OPTIMIZATION
Capacity Management
Capacity · forecasting · rightsizing
OWNS
Rightsizing agents
Capacity forecast
Home-of-Best-Fit advisor
INTELLIGENT OPS
AIOps Platform
The substrate — not the people
OWNS
Telemetry backplane · data · chatbot
Agent framework & runtime
IntOps engineers sit in the pod core
PROVIDES →
APIs · Portal · Primitives
← EMITS / PUBLISHES
IaC modules · Offering spec · Gaps
PROVIDES →
Forecasts · Rightsizing PRs
← EMITS / PUBLISHES
Telemetry · Cost · Workload patterns
PROVIDES →
Tooling · Prevention signals
← EMITS / PUBLISHES
Telemetry · Platform agent · Gaps
SQL SERVER POD
Fully dedicated · carries the pager
Pod Lead
Engineering
Ops
SQL SMEs
SRE
Intelligent Ops
Tigers — R&C
Automation is what all of them do
POD — ZEPHYR CONTROL PLANE
Self-serve by default
Pod publishes IaC modules & offerings
Self-service via control plane
Policy gates as code · controls inherited
Evidence auto-generated
POD — OPTIMIZATION
Rightsized by default
Capacity headroom visible
Rightsizing PRs in repo
Real-time usage visibility
Migration tooling on demand
POD — INCIDENT PREVENTION
Resilient by default
Anomalies surfaced before impact
Remediation proposed as PRs
Alert noise auto-triaged
SQL Server Pod | Zephyr On-Prem Program

## Slide 8
CONTROL PLANE INTEGRATION
SQL Server in the catalog
Where the integration actually happens. The pod publishes; the Control Plane renders, gates, executes and evidences.
TOUCHPOINT
THE POD DOES
THE CONTROL PLANE DOES
1
Module registry
Authors golden Terraform/OpenTofu + Ansible; publishes versioned modules with a declared contract
Hosts, versions, resolves dependencies
2
Catalog offering
Defines the offering and tiers, parameters, entitlements, approvals, chargeback
Renders it in the portal as a request
3
Policy engine
Authors SQL-specific policy-as-code: version N-1, encryption, HA tier, tagging, backup mandatory
Enforces at plan time; blocks the apply
4
Day-2 lifecycle
Defines the actions: scale, patch, restore, refresh, decommission
Exposes as catalog actions; holds state; detects drift
5
Evidence hooks
Nothing extra — evidence is a byproduct
Emits who requested, who approved, what plan, which policies passed
TIERED, NOT GENERIC
Offerings, not one "SQL Server"
Standalone-Dev · HA-Prod (AG) → standard HA/DR tiers
One generic offering invites bespoke design per request
THIN SLICE FIRST
Open the pipe, then widen it
Simplest offering through all 5 touchpoints by day 30
Riskiest integration earliest, cheapest content
Depth after the loop closes — never before
THE LINE WE HOLD
The pod does not build a portal
Name the escape hatch: % bespoke vs. paved-road is a KPI
If the pod ever builds a portal, P1 has failed
SQL Server Pod | Zephyr On-Prem Program
Notes: The escape hatch matters: pretending there is no exception path just drives it underground into the side channel.

## Slide 9
COVERAGE
Migration — the multiplier on every goal
Automated provisioning only ever helps instances that don't exist yet. The estate we already run is where the toil actually is.
Toil reduction = per-instance saving × COVERAGE. The deck so far only argues the first term. Coverage is the multiplier — and on day 1 it is zero. A golden module that carries twenty new builds while nine hundred existing instances are still patched by hand moves estate toil by noise.
Light-touch migration
Bring what exists under management
Inventory, agent, policy evaluation — no rebuild, no outage
Instance stays where it is; it just stops being invisible
Cheap, scriptable, and doable at estate scale inside 90 days
UNLOCKS: patch · drift · evidence · monitoring toil
Full codification
Rebuild onto the IaC lifecycle
Provisioned and managed end-to-end via the golden module
State imported; the instance becomes reproducible
Slow, disruptive, needs a change window per instance
UNLOCKS: everything — scale, rebuild, full lifecycle
THE 90-DAY PLAY
Go wide before deep
Light-touch migration at scale — this is where the visible toil number comes from
Codify new builds by default from day 45
Codify one cohort of existing instances to learn the cost per instance
That cost per instance is what sizes the wave-2 business case
THE CAPACITY REALITY
Migration is a third claim on the same people. The pod is not splitting between BAU and improvement — it is splitting three ways: keep the lights on, build the road, move the estate onto it. Migration is the one that gets dropped first because it is the least urgent and the most valuable. The pod lead's call on who burns toil now includes who migrates, and the board makes all three visible.
SQL Server Pod | Zephyr On-Prem Program
Notes: The honest version: if bulk light-touch migration is not feasible on our estate, the 90-day toil targets have to come down and we should say so on day 0, not day 90.

## Slide 10
CONTRACT MECHANICS
How the placeholder actually works
Placeholders are brought in by plan, not by ticket. Because there is no allocation, the contract is measured in timeliness — did they show up when the work needed them.
THE TERMS
In by plan, not by ticket
Named individual + named backup
Engagement window agreed at the charter, against the milestones
Standing invite to pod ceremonies while their work is live
Unplanned need: engage in 1 day, gap triaged in 2, dated in 5
Escalation: pod lead → squad lead → program
THE GAPS ARROW
Blocked → raise, don't route around
Gap lands in Zephyr's backlog, cross-linked
Never a spreadsheet the pod maintains
Prioritized at the monthly contract review
Owning the gap is one step from fixing it yourself
RECIPROCAL
What the pod owes back
The SQL Server offering pattern as a reusable artifact
The template every future stateful service inherits
The pod is a co-author, not a customer
This is P3 in disguise
THE NO-WORKAROUND RULE — NON-NEGOTIABLE
If the pod is blocked by a Control Plane gap: raise the gap and stop that thread. Do not route around it. This will feel wrong to good engineers — routing around a blocker is their instinct, and normally a virtue. Here it costs us the thing we came for: it makes the pod look fine while the seam stays broken, hides the gap the next engine would hit too, and then becomes permanent. A blocked thread with a raised gap is a good outcome, not a failure to deliver.
THE DIAGNOSTIC — PULL-INS SHOULD DECLINE
Days 0-30 frequent (bootstrapping the offering shape — real and expected) · days 61-90 rare. Still pulling Zephyr in weekly at day 90 → the Control Plane is a toolkit, not a product → P1 fails. That is a finding about the model, not a failure of the pod.
SQL Server Pod | Zephyr On-Prem Program

## Slide 11
HOW WE OPERATE · INTAKE
One board, one front door
If work reaches the pod any other way, the pilot is unmeasurable — and unmeasurable is how a pilot fails ambiguously.
REQUEST
LoB, project, or internal — one intake form, one queue
→
TRIAGE
Pod lead classifies, sizes, and sequences. The pod lead can say no
→
BOARD
Tagged by work type, source, toil-vs-value, agent-eligible
→
DELIVERED
Through the paved road wherever the paved road exists
THE CANARY
Side-channel work is the metric, not the nuisance
A Teams DM to a DBA. A hallway ask. A favour for an old stakeholder.
Every one of them is invisible work that never hits the board — so toil % is wrong, throughput is wrong, and the day-90 numbers are fiction
Rising side-channel % is the leading indicator that the org is rejecting the model — so we measure it deliberately rather than police it
Baseline it before day 0: how many channels does SQL work arrive through today?
WHAT IT TAKES TO HOLD
The front door needs teeth
Communicated to LoBs and stakeholders before day 15 — not assumed
The pod lead has explicit authority to redirect work to the board
Leaders in this room have to model it: if you route around it, everyone will
Emergencies still get in — they get in through the door, logged, and tagged
SQL Server Pod | Zephyr On-Prem Program

## Slide 12
HOW WE OPERATE · THE BOARD
The Jira board — what has to be built
This is a day-15 deliverable, not admin. Without it, nothing downstream can be measured.
WORK TYPES
Five, no more
Feature / enhancement
BAU request
Incident — raised by SRE into the same backlog
Compliance / patch
Toil elimination — protected
FIELDS
What makes measurement possible
Work type
Source / requester
Toil vs. value
Agent-eligible
Paved-road vs. bespoke
DISCIPLINE
Agreed before work starts
Definition of Ready / Definition of Done
WIP limits
Toil taxonomy agreed day 15 — by work type, not self-assessment
Tagging compliance is a KRI (<95% fires)
DECISION NEEDED
Start clean, and snapshot the old backlog as baseline (recommended — migrated history pollutes flow metrics and you can never tell whether lead time improved or the queue was just re-labelled) vs. migrate in-flight work.
"Toil elimination" as a first-class work type is the mechanism behind "anyone with cycles automates". If it isn't on the board, it's invisible background effort — and invisible effort is the first thing BAU eats.
SQL Server Pod | Zephyr On-Prem Program

## Slide 13
HOW WE OPERATE · THE INSTRUMENT
Mission Control
THE BOARD
Where work lives
Every item, tagged. The source of truth for flow and toil.
→
MISSION CONTROL
Where the truth about it shows up
Toil reduction · incident reduction · KRI triggers.
WHAT IT SHOWS
The pod's scoreboard
Toil % — the north star, by pool
Incident reduction and MTTR trend
Flow: lead time, throughput, WIP
Every KRI against its trigger
WHO READS IT
One view, three audiences
The pod — daily, in standup
Contract review — monthly, with liaisons
Zephyr On-Prem Program — monthly status
The 30/60/90 gates run off it
WHAT IT REPLACES
The status deck
The exec report is a Mission Control view, not a deck
Nobody hand-builds a weekly pack
A toil-reduction pod generating reporting toil is its own punchline
THE DEPENDENCY NOBODY PLANS FOR
Mission Control is only as honest as the board beneath it. It can only show toil reduction if every Jira item is tagged toil-vs-value. No tagging → no toil metric → no north star → no pilot. That makes board hygiene a day-15 deliverable and tagging compliance a KRI at 95%, not a nice-to-have. A dashboard with a hole in its data doesn't look broken — it looks like an answer, which is worse.
SQL Server Pod | Zephyr On-Prem Program

## Slide 14
HOW WE OPERATE · GOVERNANCE
Operating rhythm and governance
Three tiers. No new governance apparatus — the program tier is the Zephyr On-Prem Program that already exists.
POD
Daily → bi-weekly
Daily standup — 15 min, the board only
Weekly backlog refinement — 45 min
Weekly ops review — SLOs, incidents, drift
Bi-weekly planning · demo · retro
Owns: the work
CONTRACT
Monthly
Pod ↔ Zephyr / IntOps / Capacity liaisons
Are the contracts actually delivering?
Gaps reviewed, prioritized, dated
Pull-in frequency and response times reviewed
Owns: the seams
PROGRAM
Monthly
Zephyr On-Prem Program governance
Monthly status on the horizontal pod — standing agenda item, own RAG
KRI escalations land here
The 30/60/90 gates and the GO / ADJUST / STOP verdict
Owns: the verdict
One pipe, not three. The monthly program report is the same Mission Control view the pod reads daily. If anyone starts assembling a program pack by hand, the pod has generated exactly the toil it exists to eliminate.
Why the pod doesn't own the verdict: a pod grading its own pilot is worthless. The verdict sits with program governance, against criteria agreed on day 0.
SQL Server Pod | Zephyr On-Prem Program

## Slide 15
HOW WE OPERATE · CAPACITY
Who burns the toil
BAU always wins a fair fight against improvement work. So we don't leave the fight fair — but we don't fix the roster either.
DISCRETION
The pod lead decides
Who burns the toil, and when — the pod lead's call
Opportunistic: whoever has cycles, automates
No fixed roster split — a fixed split is an automation team with a spreadsheet
Dynamic week to week as BAU ebbs and flows
VISIBILITY
The board makes it visible
"Toil elimination" is a first-class work type
Protected time shows up as items, not intentions
Toil % tracked weekly in Mission Control
Invisible effort is the first thing BAU eats
SAFETY NET
The KRI is the backstop
Toil-elimination capacity below threshold for 2 consecutive weeks → KRI fires
Escalates to Zephyr On-Prem Program governance
Surfaces a slow BAU squeeze at day 30, not day 60
Discretion with a tripwire — not a rule
WHY NOT A FIXED RINGFENCE
Because ringfencing by people builds an automation team by accident, whatever we call it.
"These three automate, those five carry BAU" is exactly the caste system we're removing — and it puts the automation in the hands of the people who don't feel the pain. The pod lead's discretion is the only version consistent with "anyone with cycles automates". The honest risk is the mirror image: if it's everyone's job, it can become nobody's job. That's what the board and the KRI are for.
SQL Server Pod | Zephyr On-Prem Program

## Slide 16
ARTIFACTS
Where all of this lives
The deck persuades. The charter governs. The board records. Mission Control reports.
ARTIFACT
HOLDS
OWNER
LIFECYCLE
Pod Charter
Mission · pod goals · pilot goals · non-goals · roster · named liaisons · no-workaround rule · verdict criteria
Pod Lead
Signed day 15
Contract sheets
What they owe / we owe · response SLA · escalation path · standing-slot terms
Lead + liaison
Reviewed monthly
Jira board
The work · the toil taxonomy · the tagging
Pod Lead
Live
Mission Control
KPI / KRI readout · trigger thresholds
Pod Lead
Live
Baseline pack
Metric · source · method · confidence, per pool
Pod + Tigers
Frozen day 30
Offering + module spec
SQL catalog offering, tiers, params, policy rules
Pod (Eng)
In the registry
Gap log
Raised control-plane and IntOps gaps, with dates
Liaison
In Zephyr's backlog
Pattern doc
P3 — what engine #2 inherits
Pod Lead
Drafted day 75
Nothing here is a new tool. Charter and contract sheets are documents; everything else is Jira, the registry, or Mission Control.
SQL Server Pod | Zephyr On-Prem Program
Notes: The Charter is the artifact that answers 'where are the pod goals defined' permanently. Signed day 15 by the pod lead, the sponsor, and each named liaison — a liaison who won't sign hasn't committed, and day 15 is a cheap place to learn that.

## Slide 17
MEASUREMENT · KPIS
North star, then three pools
The rule: if it can't be pulled automatically from Jira, Git, the registry, Mission Control or telemetry — it isn't on the list. Hand-collected metrics die in week three.
NORTH STAR
Toil % — the share of pod capacity spent on manual, repetitive, automatable, reactive work
KPI
POOL
SOURCE
BASELINE
% estate migrated — under patch/evidence automation
Coverage
Mission Control
Required
% estate codified — full IaC lifecycle
Coverage
Zephyr registry
Required
Provisioning lead time · self-service rate
Operations
Zephyr + Jira
Required
Patch cycle time · SLA compliance
Operations
Zephyr Assurance
Required
Golden module reuse count
Operations
Zephyr registry
—
Evidence person-hours per audit cycle
Compliance
Tigers + Jira
Required
Evidence auto-assembly % · drift remediation time
Compliance
Zephyr Assurance
Required
Alert-to-incident ratio (noise)
Incidents
IntOps
Required
Incidents · MTTR · repeat-incident %
Incidents
IntOps
Required
Agent PRs proposed / approved / rejected
All (P2)
GitHub
—
Zephyr pull-ins per week · response time
Contracts (P1)
Pod board
—
% work through the front door
Model (G4)
Jira
Required
Consumption, not production. "Modules published" is vanity. "Provisions through the module" is real — the model's whole claim is that things get consumed, not built twice.
SQL Server Pod | Zephyr On-Prem Program

## Slide 18
MEASUREMENT · HONESTY
Two ways these numbers could lie
Both of these will be raised at us. Better we raise them first — a metric whose weakness we named ourselves survives scrutiny; one that gets exposed takes the whole board down with it.
TRAP 1
Toil % is self-reported — and gameable
The people tagging the work are the people being measured on it
Toil can "fall" 20% through reclassification alone, with nothing changing
Fix: define toil by work type — automatable, repetitive, reactive — not by self-assessment
Taxonomy agreed day 15, before anyone knows which way the numbers need to go
Spot-audit a sample each month; Tigers is well placed to do it
TRAP 2
Incident counts drop for reasons that aren't us
Change freezes, seasonality, and less delivery all reduce incidents
We could claim a win for a quiet quarter we had nothing to do with
Fix: normalize per change and per instance, not raw counts
Pair with repeat-incident % — far harder to fake and closer to what we actually claim
12 months of history for the baseline, so seasonality is visible
The rule underneath both: anything we can't baseline, we don't claim. If a number isn't recoverable, we either instrument it forward from day 15 or drop the claim entirely. A soft number sitting next to hard ones on the day-90 slide contaminates all of them.
This slide is deliberately in the deck rather than the appendix. The fastest way to lose a governance room is to present a number it can break in one question.
SQL Server Pod | Zephyr On-Prem Program

## Slide 19
MEASUREMENT · KRIS
What would kill this — and when we'd know
A KRI without a threshold is a chart nobody acts on. Each one below has a trigger and an escalation route.
RISK INDICATOR
TRIGGER
WHY IT KILLS YOU
Side-channel work %
> 10% and rising
The canary — the organization is rejecting the model
BAU crowding out toil work
> 40% unplanned
The classic pilot killer: pod busy, nothing shipped
Board tagging compliance
< 95%
Mission Control goes blind; the north star evaporates
Blocked on a horizontal
any item > 5 days
The contracts are gates after all — P1 failing at the seam
Agent PR rejection rate
> 40% or < 5%
High = noise. Low = rubber-stamping — an E-23 problem, not a win
Baseline / CMDB confidence
< 90%
If the baseline is wrong, every downstream number is wrong
Change fail rate
rising vs. baseline
We're going faster by being reckless
Regrettable attrition
any
People vote with their feet before they vote in a survey
The rejection floor deserves the attention: a suspiciously low reject rate doesn't mean the agents are brilliant — it means humans stopped reading. Tigers owns this KRI, from inside the pod. That is the single best argument for Risk & Compliance sitting in the pod rather than reviewing it from outside.
SQL Server Pod | Zephyr On-Prem Program

## Slide 20
MEASUREMENT · BASELINES
The baseline — captured and frozen by day 30
Provenance matters as much as the number. Every line declares whether it's system-derived, sampled, or recalled.
POOL
WHAT WE CAPTURE
SOURCE
METHOD
CONFIDENCE
Estate
Instances by version, edition, env, LoB, criticality · allocated vs. used · orphans · licence position
CMDB + discovery
System
High
Estate
CMDB-vs-discovery delta — a baseline metric in its own right
Both
System
High
Operations
Provisioning lead time + touch hours, hand-offs, teams involved
ServiceNow / Jira
Sample last 20-30
Medium
Operations
Patch cycle time, hours per cycle, SLA %, deferrals, rollback rate
Zephyr Assurance
System
High
Operations
Restores and dev refreshes — volume + hours
Ticket history
Sample
Medium
Compliance
Evidence person-hours per audit cycle · artifacts per cycle · findings
Tigers
Recalled
Low
Compliance
Drift findings + time to remediate · open exceptions + aging
Zephyr Assurance
System
High
Incidents
Incidents by severity over 12 months · MTTR · repeat-incident %
IntOps
System
High
Incidents
Alert volume · alert-to-incident ratio · after-hours pages per engineer
IntOps
System
High
Model
How many channels SQL work arrives through today
Survey
Sample
Low
SQL Server Pod | Zephyr On-Prem Program
Notes: Low confidence on evidence hours is fine — the target is -50%, so plus or minus 30% still shows it. Say that rather than pretending precision.

## Slide 21
MEASUREMENT · BASELINES
Two traps in the baseline itself
TRAP 1
Sample, don't census
20-30 provisioning requests, not all of them
A perfect baseline is no baseline — it eats the pilot it was meant to measure
Timebox to day 30. Freeze it. Sign it. Move on
Disputed numbers are a finding (that's D1), not a reason to keep counting
TRAP 2 — THE BIG ONE
The audit-calendar trap
G2 is measured in evidence hours per audit cycle
If there is no audit cycle inside the 90 days, we can't show compliance toil falling — run the evidence drill instead
Check the calendar now, not at day 60
THE FIX — AN EVIDENCE DRILL
A timed, simulated evidence request at day 30 and again at day 85 — same scope both times. Clean before-and-after, independent of the audit calendar, and honestly more rigorous than a real cycle because the scope is controlled rather than whatever the auditor happened to ask for this year. Tigers runs it — they're in the pod, which is what makes this cheap. Consider the same mechanism for provisioning if request volume in the window is too low to sample meaningfully.
Why this slide exists: the baseline is the only part of this pilot that cannot be redone later. Everything else can be adjusted at day 60. Get this wrong and the day-90 conversation is about methodology instead of outcomes — which is how a pilot fails ambiguously.
SQL Server Pod | Zephyr On-Prem Program

## Slide 22
THE 90 DAYS
Milestones — every gate has a tell
Each gate states what must be true. If it isn't true, we adjust — that's the point of having gates rather than a launch date.
DAY 15
Stand up
MUST BE TRUE
Pod chartered; lead named with authority to say no
Core named, allocations confirmed in writing
Liaisons named as individuals + backups
Board live; front door closed and communicated
Toil taxonomy agreed
Can't name everyone → the model has already told us something
DAY 30
Baseline & first loop
MUST BE TRUE
Baseline captured, frozen and signed
Metrics flowing automatically — no hand-collection
Thin-slice offering live in the catalog
One real request fulfilled end-to-end
Still hand-collecting → day 90 proves nothing
DAY 45
Paved road real
MUST BE TRUE
Golden module live in the registry
First real provision with no human touching the build
Migration underway — first cohort under management
Patch agent proposing PRs in non-prod
Module works but coverage flat → we built a road with no traffic
DAY 60
The decision gate
MUST BE TRUE
Migration at scale — coverage is the number to watch
All three pools trending
Agent approve/reject rates meaningful
Mission Control is the readout
GO / ADJUST call for the final 30 days
DAY 90
Readout
MUST BE TRUE
Evidence against every goal
The pattern doc
Verdict at program governance
GO / ADJUST / STOP
Day 90 is the readout. Day 60 is the decision. If we wait until day 90 to discover a problem, we have no time to do anything about it. Day 60 is where a month still remains to change the answer. (Day 75, soft: freeze scope and start the pattern doc — one written in the last 48 hours is a fiction.)
SQL Server Pod | Zephyr On-Prem Program

## Slide 23
THE 90 DAYS
What we put on the table at day 90
THE EVIDENCE
Against every goal, from the instrument — not a narrative
Toil % vs. baseline — broken out per pool, so ops, compliance and incidents stand or fall separately
% of the estate migrated onto the automated pattern — the multiplier on every other number
Provisioning lead time and self-service rate vs. baseline (G1)
Evidence person-hours per audit cycle — or the day-30 vs. day-85 drill (G2)
Alert-to-incident ratio, repeat-incident %, MTTR (G3)
% work through the front door · side-channel trend (G4)
Golden module reuse count — provisions through it, not modules published (P1)
Zephyr pull-ins per week — the taper, or the absence of one (P1)
Agent PRs proposed / approved / rejected, with the rejection rate in both directions (P2)
The pattern doc — what engine #2 inherits (P3)
Squad health and retention
NOT PROMISED
What we said on day 0 we would not show
Estate-wide cost savings
Headcount impact
Migrations complete
Other engines onboarded
Outcome metrics at full maturity — those need 2-3 quarters of signal, not 90 days
Saying this up front is what makes the rest credible. If we promise outcome metrics at day 90, we fail on arithmetic rather than on merit — and the model takes the blame for a calendar.
SQL Server Pod | Zephyr On-Prem Program

## Slide 24
THE 90 DAYS
GO · ADJUST · STOP
Criteria agreed today, not argued at day 90. The verdict sits with Zephyr On-Prem Program governance.
GO
The model worked and the pattern is repeatable
Toil down materially across at least two pools
Contracts held — pull-ins tapered, no shadow rebuilds
Pattern doc is usable by another team
→ Charter engine #2
ADJUST
The model works — our execution was wrong
Under-resourced, BAU crowding, liaisons unnamed or unresponsive, baseline weak
The structure is sound; the conditions weren't
→ Fix and re-run. This is not a model failure
STOP
The structure genuinely doesn't fit the work
Pod ownership didn't hold even when properly resourced
Contracts couldn't be made to work as products
→ A real signal. Redesign rather than repeat
MODEL FAILURE VS. EXECUTION FAILURE
Most pilots that "fail" are ADJUST wearing a STOP costume. Separating the two is the single most protective thing in this deck — and the reason the criteria have to be pre-committed is that the body holding the verdict is also accountable for the dependency most likely to sink the pilot. The dated gap log is what makes "the model works, the platform needs another quarter" a finding rather than a blame conversation.
The real risk isn't failing — it's failing ambiguously. Ambiguity gets filled by whoever had the strongest prior, and the loudest voice in the room wins a question the evidence should have answered.
SQL Server Pod | Zephyr On-Prem Program

## Slide 25
RISKS AND THE ASK
What could go wrong — and what we need
THE CRITICAL PATH — DAY 15
Liaisons named as individuals, board live with the toil taxonomy agreed, front door closed. None of it is glamorous and all of it is load-bearing: no names means the contracts are queues, no tagging means Mission Control is blind, and no front door means the flow numbers are fiction. Day 15 slipping doesn't delay day 90 — it makes day 90 unprovable.
Control plane gaps surface late
Blocks the pod mid-pilot; the contract stalls
Mitigation: Gaps raised not routed around; triaged in 2 days, dated in 5
BAU crowds out the toil work
Pod busy, nothing shipped, day 45 gate slips
Mitigation: Board visibility + KRI escalating to program
Liaisons never actually named
The contract is a queue in disguise
Mitigation: Named individual + backup by day 15, or escalate
Baseline quality
Wrong baseline → every downstream number wrong
Mitigation: Freeze and sign at day 30; CMDB delta is itself a finding
Rubber-stamping the agents
E-23 exposure dressed as efficiency
Mitigation: Rejection-rate floor as a KRI, owned by Tigers
Diffusion of the toil work
"Anyone can automate" becomes nobody did
Mitigation: First-class work type on the board; pod lead protects it
THE ASK: 1. Name the liaisons by day 15 — individuals, with backups 2. Back the pod lead's call on who burns toil 3. Agree the GO / ADJUST / STOP criteria — today
SQL Server Pod | Zephyr On-Prem Program
Notes: Close on the ask. Do not leave the room without the verdict criteria agreed — that is the one thing that cannot be added later.