## WBS (Master)
IaC via DBaaS API — Granular Work Breakdown Structure (Ansible-orchestrated, AI-SDLC mapped)
9 workstreams · ~65 tasks · covers architecture decisions, control-plane enablement, provisioning, migration (Debezium CDC), testing, day-2 ops, decommission. Ownership: Manual / AI-SDLC / AI + human gate.
WBS ID | Workstream | Task | Detail / Sub-tasks | Architecture Pattern / Decision | Ownership | Key Artifact | Depends On
1.1 | WS1 · Foundation & Architecture | Choose control-plane interaction model | Decide declarative reconcile (converge to desired state) vs imperative call-and-forget. Declarative wins for audit + idempotency. | Reconciliation-oriented; desired-state in Git is source of truth | Manual | ADR: interaction model | —
1.2 | WS1 · Foundation & Architecture | Select state-management approach | No local mutable state; Git spec + live DBaaS state are the two poles. Diff drives action. Avoid a drifting state file. | Git-as-truth; stateless reconcile loop | Manual | ADR: state mgmt | 1.1
1.3 | WS1 · Foundation & Architecture | Design idempotency strategy | Deterministic naming + external/correlation IDs + GET-before-POST so re-runs converge, never duplicate. | Idempotency key pattern; GET-before-POST | AI + gate | Idempotency design note | 1.1
1.4 | WS1 · Foundation & Architecture | Design async-operation handling | DBaaS provisioning is long-running. Operation IDs, poll-until-terminal, exponential backoff, hard timeout, saga/compensation on FAILED. | Async polling + saga/compensation | AI + gate | Async-op design | 1.1
1.5 | WS1 · Foundation & Architecture | Credential & secrets architecture | Short-lived tokens from Vault/broker, role-bound, time-boxed, never inlined. Per-operation scope. | Credential broker pattern; just-in-time secrets | Manual | ADR: secrets | —
1.6 | WS1 · Foundation & Architecture | Orchestration layer choice | Temporal-fronted Ansible (durable workflows, retries, visibility) vs AWX/Tower. Temporal gives compensation + audit lineage. | Temporal-fronted Ansible execution layer | Manual | ADR: orchestration | 1.4
1.7 | WS1 · Foundation & Architecture | Egress & network architecture | Define egress from execution env to DBaaS API + DB endpoints: subnets, firewall, private link / egress gateway. | Controlled egress; private connectivity | Manual | Network design | —
1.8 | WS1 · Foundation & Architecture | TLS & auth design | mTLS to control plane; SCRAM-SHA-512 to MariaDB; certificate lifecycle & rotation. | mTLS + SCRAM-SHA-512; cert rotation | Manual | Security design | 1.5
1.9 | WS1 · Foundation & Architecture | Policy-as-code architecture | Gate on approved versions, mandatory encryption-at-rest, placement/region rules, naming. Enforced pre-mutation. | Policy-as-code gate (OPA/Conftest) | AI + gate | Policy baseline | —
1.10 | WS1 · Foundation & Architecture | Drift & reconciliation architecture | Detect loop cadence, drift classification (low vs high blast radius), and who holds execution authority for remediation. | Closed-loop reconcile; risk-tiered authority | Manual | ADR: drift model | 1.2
1.11 | WS1 · Foundation & Architecture | Observability & audit architecture | Provenance trail for every action, change records, telemetry. Critical for SR 11-7-style lineage on autonomous actions. | Audit-grade provenance; immutable trail | Manual | Audit design | 1.6
1.12 | WS1 · Foundation & Architecture | Environment topology & blast radius | dev/test/prod isolation, tenancy boundaries, promotion path, blast-radius containment. | Environment isolation; progressive promotion | Manual | Topology design | —
2.1 | WS2 · Control-Plane Enablement | Provision orchestration runtime | Stand up Ansible execution env / Temporal workers on OpenShift; HA, autoscaling, resource quotas. | Containerized execution env on OpenShift | AI + gate | Runtime manifests | 1.6
2.2 | WS2 · Control-Plane Enablement | Stand up secrets backend & broker | Deploy/integrate Vault; configure roles, leases, dynamic secrets, broker endpoints. | Dynamic secrets; least-privilege roles | AI + gate | Vault config | 1.5
2.3 | WS2 · Control-Plane Enablement | Configure egress & firewall | Open egress to DBaaS API + DB ports; private link; deny-by-default baseline. | Deny-by-default + explicit allow | AI + gate | Firewall/egress rules | 1.7
2.4 | WS2 · Control-Plane Enablement | Establish API service accounts | Least-privilege roles/scopes per environment; separate identities for provision vs day-2. | Least-privilege service identities | Manual | IAM bindings | 1.8
2.5 | WS2 · Control-Plane Enablement | Build pinned execution-env image | Ansible collections + dependencies version-pinned; reproducible image; supply-chain scan. | Pinned, reproducible build; SBOM | AI-SDLC | EE image + SBOM | 2.1
2.6 | WS2 · Control-Plane Enablement | Wire GitOps CI/CD pipeline | PR triggers, environment promotion, required checks, gated merges, artifact signing. | GitOps; gated promotion | AI + gate | Pipeline config | 2.5
2.7 | WS2 · Control-Plane Enablement | Bootstrap policy-as-code repo | Encode baseline policies from 1.9 as testable rules in CI. | Policy-as-code in CI | AI-SDLC | Policy repo | 1.9
3.1 | WS3 · Spec & Authoring | Define spec schema | JSON-schema for desired-state YAML: engine, version, profile, HA, network, params, SLA, owners, cost center. | Schema-validated declarative spec | AI + gate | spec.schema.json | 1.2
3.2 | WS3 · Spec & Authoring | Author spec template & examples | Golden-path templates + per-tier examples; inline guidance. | Golden-path templates | AI-SDLC | spec templates | 3.1
3.3 | WS3 · Spec & Authoring | Build spec validation | Schema validation + semantic checks (valid profile, approved version, SLA tier exists). | Two-layer validation (syntax+semantic) | AI-SDLC | validate task/CI step | 3.1
3.4 | WS3 · Spec & Authoring | Catalog approved profiles | Compute profiles, parameter-group presets, SLA tiers, backup policies — curated, governed. | Curated catalog; opinionated defaults | Manual | profile catalog | 3.1
4.1 | WS4 · Provisioning Pipeline | Token-mint task | Pull short-lived bearer token from broker at run time; no_log; in-memory only. | JIT credential; no_log | AI-SDLC | auth task | 2.2
4.2 | WS4 · Provisioning Pipeline | Pre-flight validation tasks | Naming, quota/capacity, subnet reachability, policy conformance — fail fast before mutation. | Fail-fast pre-flight gate | AI-SDLC | preflight role | 2.7,3.3
4.3 | WS4 · Provisioning Pipeline | Idempotency check (GET-before-POST) | Query for existing instance matching spec/correlation ID; skip create if present. | GET-before-POST idempotency | AI-SDLC | check task | 1.3
4.4 | WS4 · Provisioning Pipeline | Provisioning POST task | POST create/clone request to DBaaS /databases; capture operation ID (202). | Declarative create via REST | AI + gate | provision task | 4.3
4.5 | WS4 · Provisioning Pipeline | Async poll loop | GET /operations/{id} with until/retries/delay/backoff + hard timeout. | Async poll w/ backoff + timeout | AI-SDLC | poll task | 1.4,4.4
4.6 | WS4 · Provisioning Pipeline | Failure handling / compensation | On FAILED: cleanup partial resources, emit alert, roll back correlation state. | Saga compensation on failure | AI + gate | compensation handler | 1.4,4.5
4.7 | WS4 · Provisioning Pipeline | Apply parameter group | Push tuned params from catalog; flag any affecting availability for human review. | Config-as-data; param presets | AI + gate | param task | 3.4,4.5
4.8 | WS4 · Provisioning Pipeline | Provision users & grants | Create app users, least-privilege grants; store creds in Vault. | Least-privilege grants | AI + gate | user/grant task | 2.2,4.5
4.9 | WS4 · Provisioning Pipeline | Set backup / time-machine SLA | Apply declared retention/RPO schedule; verify it took effect. | SLA-driven backup policy | AI-SDLC | backup task | 4.5
4.10 | WS4 · Provisioning Pipeline | Register monitoring/observability | Attach metrics/log agents, alerts, dashboards to the new instance. | Observability-on-create | AI-SDLC | monitoring task | 4.5
5.1 | WS5 · Migration Workstream | Migration assessment & classification | Classify each DB: lift-shift vs re-platform; engine/version compatibility; size; downtime tolerance. | Assessment-first; wave planning | AI + gate | migration assessment | 3.4
5.2 | WS5 · Migration Workstream | Schema inventory & dependency map | Enumerate schemas, objects, FKs, stored procs, triggers, jobs; map cross-DB dependencies. | Dependency-aware sequencing | AI-SDLC | inventory + dep map | 5.1
5.3 | WS5 · Migration Workstream | Schema conversion (AI-assisted) | Translate DDL / incompatible types / proc syntax to target engine. AI drafts, surfaces ambiguities. | AI-assisted schema conversion | AI + gate | converted DDL | 5.2
5.4 | WS5 · Migration Workstream | Schema conversion review | Human review of converted objects, esp. procs/triggers/edge types; sign-off before load. | Mandatory human review of conversion | Manual | review sign-off | 5.3
5.5 | WS5 · Migration Workstream | Provision migration target | Reuse WS4 pipeline to stand up the target instance from spec. | Reuse provisioning pipeline | AI + gate | target instance | 4.4
5.6 | WS5 · Migration Workstream | Initial bulk load / snapshot | Consistent snapshot + bulk load of baseline data to target. | Snapshot + bulk seed | AI-SDLC | seeded target | 5.4,5.5
5.7 | WS5 · Migration Workstream | Deploy Debezium connector | KafkaConnect CR via Strimzi/AMQ Streams on OpenShift; MariaDB source connector image. | Strimzi KafkaConnect CR pattern | AI + gate | KafkaConnect CR | 5.5
5.8 | WS5 · Migration Workstream | Configure CDC source | MariaDB binlog (ROW), unique server-id, TLS + SCRAM-SHA-512, external Kafka/DB endpoints, egress. | CDC source: binlog + TLS/SCRAM | AI + gate | connector config | 5.7,1.8
5.9 | WS5 · Migration Workstream | Configure CDC sink / apply | Stream changes to target; ordering, idempotent apply, DLQ for poison records. | Idempotent sink + DLQ | AI + gate | sink config | 5.6,5.8
5.10 | WS5 · Migration Workstream | Data reconciliation & validation | Row counts, checksums/hash-diff, lag monitoring until target is caught up & consistent. | Continuous reconcile; lag SLO | AI-SDLC | recon report | 5.9
5.11 | WS5 · Migration Workstream | Cutover planning | Freeze window, MaxScale/DNS routing-flip plan, app connection-string change, comms. | Routing-flip cutover; freeze window | Manual | cutover runbook | 5.10
5.12 | WS5 · Migration Workstream | Cutover execution | Quiesce writes, drain CDC lag to zero, flip MaxScale/DNS to target, resume. | Drain-to-zero then flip | Manual | cutover executed | 5.11
5.13 | WS5 · Migration Workstream | Rollback plan & criteria | Pre-defined abort triggers; reverse routing to source; keep source live through bake period. | Reversible cutover; bake period | Manual | rollback plan | 5.11
5.14 | WS5 · Migration Workstream | Post-cutover validation | App smoke tests, perf check, data spot-checks; only then decommission source (WS9). | Bake + validate before teardown | AI + gate | validation evidence | 5.12
6.1 | WS6 · Testing & Assurance | Role unit / molecule tests | Per-role tests with mocked API; scenario matrix. | Molecule + mocked control plane | AI-SDLC | molecule suite | 2.5
6.2 | WS6 · Testing & Assurance | Negative & error-path tests | Quota-exceeded, auth-fail, timeout, partial-failure compensation. | Negative-path coverage | AI-SDLC | negative tests | 6.1
6.3 | WS6 · Testing & Assurance | Idempotency re-run test | Run twice; assert converge, no duplicate, no diff on second pass. | Convergence assertion | AI-SDLC | idempotency test | 4.3
6.4 | WS6 · Testing & Assurance | Drift-scenario test | Inject out-of-band change; assert detection + correct classification. | Drift injection test | AI-SDLC | drift test | 1.10
6.5 | WS6 · Testing & Assurance | Restore-drill validation | Actually restore from backup to a scratch instance; verify integrity. Backup SLA isn't real until this passes. | Prove-the-restore drill | AI + gate | restore evidence | 4.9
6.6 | WS6 · Testing & Assurance | Security & conformance scan | CIS/STIG checks, encryption, exposed-port scan, secret-leak scan. | Conformance scanning in CI | AI-SDLC | scan report | 2.7
6.7 | WS6 · Testing & Assurance | Performance / load validation | Post-migration perf parity vs source baseline; param tuning verification. | Baseline-parity load test | AI + gate | perf report | 5.14
7.1 | WS7 · SoR Registration & Deploy | CMDB registration | Create/Update CI in ServiceNow with relationships & ownership. | SoR registration | AI-SDLC | CMDB CI | 4.5
7.2 | WS7 · SoR Registration & Deploy | IPAM registration | Reserve/record IP allocation. | IPAM sync | AI-SDLC | IPAM record | 4.5
7.3 | WS7 · SoR Registration & Deploy | Vault secret storage | Persist app/admin creds + rotation policy. | Centralized secret store | AI-SDLC | stored secrets | 4.8
7.4 | WS7 · SoR Registration & Deploy | Cost / FinOps tagging | Cost center, owner, env, SLA tier tags for attribution. | Tag-driven cost attribution | AI-SDLC | cost tags | 4.5
7.5 | WS7 · SoR Registration & Deploy | Change-record generation | Auto-draft change record with diff, risk, blast radius for approval. | Auto change record | AI + gate | change record | 4.4
7.6 | WS7 · SoR Registration & Deploy | Promotion approval & deploy | Human approves prod promotion / change window; pipeline executes. | Human promotion gate | Manual | approved deploy | 6.5,7.5
8.1 | WS8 · Operate / Day-2 | Drift detection loop | Scheduled compare of live state vs Git spec across fleet. | Closed-loop drift detect | AI-SDLC | drift report | 1.10
8.2 | WS8 · Operate / Day-2 | Drift classification | Tag each drift low vs high blast radius (availability/retention = high). | Risk-tiered classification | AI-SDLC | classified drift | 8.1
8.3 | WS8 · Operate / Day-2 | Low-risk auto-remediation | Snap reversible/non-impacting drift back to spec automatically. | Auto-heal (reversible only) | AI-SDLC | remediation log | 8.2
8.4 | WS8 · Operate / Day-2 | High-risk reconciliation proposal | AI proposes fix; routes to same approval gate as a human change. AI never executes high-risk unattended. | Propose-not-execute; human gate | AI + gate | reconcile proposal | 8.2
8.5 | WS8 · Operate / Day-2 | Patch management | Plan + apply engine/OS patches via idempotent playbook in window. | Idempotent patch in window | AI + gate | patch run | 7.6
8.6 | WS8 · Operate / Day-2 | Scale operations | Vertical/horizontal scale via API; validate no SLA breach. | API-driven scaling | AI + gate | scale run | 7.6
8.7 | WS8 · Operate / Day-2 | Failover drills | Scheduled HA failover test; measure RTO; capture evidence. | Game-day failover drill | AI + gate | drill evidence | 7.6
8.8 | WS8 · Operate / Day-2 | Recurring restore validation | Periodic restore-drill (not just at build). Standing assurance. | Recurring restore proof | AI + gate | restore evidence | 6.5
8.9 | WS8 · Operate / Day-2 | Runbook & postmortem generation | Auto-draft runbooks and incident postmortems from telemetry. | AI-drafted ops docs | AI-SDLC | runbooks/PMs | 1.11
9.1 | WS9 · Decommission | Decommission request & approval | Capture request; mandatory human sign-off (irreversible). | Human sign-off required | Manual | approved request | —
9.2 | WS9 · Decommission | Final snapshot | Take + verify final snapshot before any delete. | Snapshot-before-delete | AI + gate | final snapshot | 9.1
9.3 | WS9 · Decommission | Honor retention / legal hold | Apply retention policy; block delete if legal hold active. | Retention/hold enforcement | Manual | hold check | 9.1
9.4 | WS9 · Decommission | Deregister CMDB / IPAM / Vault | Remove/retire CI, release IP, revoke/retire secrets. | SoR deregistration | AI-SDLC | deregistered records | 9.2
9.5 | WS9 · Decommission | Release resources & tags | Delete instance via API; release compute/storage; clear cost tags. | Clean resource release | AI + gate | released resources | 9.2,9.3
9.6 | WS9 · Decommission | Archive audit trail | Persist full provenance + change records to immutable archive. | Immutable audit archive | AI-SDLC | archived trail | 9.5

## Architecture Patterns
Architecture Patterns — Decisions, Recommended Approach, Anti-patterns
Pattern | Problem It Solves | Recommended Approach | Anti-pattern to Avoid | AI-SDLC Role | WBS Ref
Reconciliation loop | Imperative scripts drift and can't prove current state | Converge live state to Git desired-state; diff drives action; re-runnable | Fire-and-forget imperative calls; mutable state file | Generate reconcile logic & diff engine | 1.1,1.2,1.10
Idempotency key / GET-before-POST | Re-runs create duplicates or fail | Deterministic naming + correlation IDs; check existence before create | Blind POST on every run | Scaffold check + dedup logic | 1.3,4.3
Async polling + saga | DBaaS ops are long-running and can half-fail | Operation IDs, poll-until-terminal w/ backoff+timeout, compensation on FAILED | Sleep-and-hope; no cleanup on failure | Generate poll loop + compensation handlers | 1.4,4.5,4.6
Credential broker (JIT secrets) | Long-lived secrets in playbooks leak | Short-lived, role-bound tokens minted at run time; no_log; in-memory | Secrets in vars/Git; static API keys | Wire token-mint task (never invents creds) | 1.5,2.2,4.1
Temporal-fronted Ansible | Need durability, retries, visibility, audit lineage | Workflow engine fronts Ansible: durable state, retries, compensation, history | Cron-driven playbooks with no audit trail | Generate workflow + activity stubs | 1.6,2.1
Controlled egress | Execution env reaching DBaaS/DB endpoints safely | Private link / egress gateway; deny-by-default + explicit allow | Open egress; public endpoints | Generate firewall/egress manifests | 1.7,2.3
mTLS + SCRAM-SHA-512 | Auth to control plane and MariaDB | mTLS to API; SCRAM-SHA-512 to DB; managed cert rotation | Plaintext / shared static passwords | Generate config, flag rotation tasks | 1.8,5.8
Policy-as-code gate | Non-conforming infra slips through | OPA/Conftest gates pre-mutation: versions, encryption, placement, naming | Manual checklist review only | Author + maintain policy rules | 1.9,2.7
Risk-tiered remediation authority | Autonomous fixes on prod are dangerous | Low-risk auto-heals; high-risk AI proposes, human executes via same gate | Letting AI execute any prod change unattended | Classify drift; draft proposals | 1.10,8.2,8.4
Audit-grade provenance | Autonomous actions need accountable lineage | Immutable trail per action + change records (SR 11-7-style lineage) | Untracked automated changes | Auto-generate change records & trail | 1.11,7.5,9.6
Environment isolation | Blast radius across dev/test/prod | Hard tenancy boundaries; progressive promotion; per-env identities | Shared creds/network across envs | Generate per-env scaffolding | 1.12,2.4

## Migration Deep-Dive
Database Migration Workstream — Debezium CDC, Stage by Stage
Near-zero-downtime pattern: assess → convert schema → seed → CDC replicate → reconcile → routing-flip cutover → bake → decommission source. Debezium on OpenShift via Strimzi/AMQ Streams KafkaConnect.
Phase | Stage | What Happens | Key Technical Detail | Ownership | Risk
A · Assess | Assessment & wave planning | Classify each DB by complexity, size, downtime tolerance; group into migration waves. | Compatibility matrix; pilot the lowest-risk wave first | AI + gate | Low
A · Assess | Schema inventory & dependencies | Enumerate objects, FKs, procs, triggers, jobs; map cross-DB coupling to order the cutover. | Dependency graph drives sequencing | AI-SDLC | Low
B · Convert | Schema conversion (AI-assisted) | AI drafts target DDL, translates incompatible types/proc syntax, flags ambiguous constructs. | Procs/triggers/custom types are the hard part | AI + gate | Med
B · Convert | Conversion review & sign-off | Human reviews converted objects before any data load. | Mandatory gate — conversion errors corrupt downstream | Manual | Med
C · Seed | Provision target | Reuse the provisioning pipeline (WS4) to build the target from spec. | Same idempotent path as net-new | AI + gate | Med
C · Seed | Initial bulk load | Consistent snapshot of source → bulk seed target as the CDC baseline. | Record the binlog position at snapshot time | AI-SDLC | Med
D · Replicate | Deploy Debezium connector | KafkaConnect CR via Strimzi/AMQ Streams; MariaDB source connector image on OpenShift. | KafkaConnect CR pattern; connector plugin in EE image | AI + gate | Med
D · Replicate | Configure CDC source | MariaDB binlog in ROW mode, unique server-id, TLS + SCRAM-SHA-512, external Kafka/DB endpoints + egress. | binlog_format=ROW; gtid; one server-id per connector | AI + gate | High
D · Replicate | Configure sink / apply | Apply change stream to target with ordering + idempotent writes; DLQ for poison records. | Idempotent apply + dead-letter queue | AI + gate | High
E · Reconcile | Validate & monitor lag | Row counts, checksums/hash-diff; watch replication lag until target is caught up. | Define a lag SLO that must hold before cutover | AI-SDLC | Med
F · Cutover | Cutover planning | Freeze window, MaxScale/DNS routing-flip plan, connection-string change, comms. | Routing flip = the actual cutover lever | Manual | High
F · Cutover | Cutover execution | Quiesce writes, drain CDC lag to zero, flip MaxScale/DNS to target, resume traffic. | Drain-to-zero before flip = near-zero data loss | Manual | High
F · Cutover | Rollback path | Pre-set abort triggers; keep source live and writable-recoverable during bake. | Reverse the routing flip; source stays warm | Manual | High
G · Bake | Post-cutover validation | Smoke tests, perf parity vs baseline, data spot-checks during bake period. | Only after bake passes does source teardown proceed | AI + gate | Med
H · Retire | Decommission source | Final snapshot + retention hold, then release source (hands to WS9). | Irreversible — human sign-off | Manual | High

## Legend
Legend & Conventions
Ownership tag | Meaning
Manual | Human owns end to end; not automated.
AI-SDLC | Fully eligible for AI generation / automated execution (reversible or low-risk).
AI + gate | AI generates/proposes & executes reversible parts; a human approval gate guards the irreversible/risk-bearing step.
Workstream bands | WS1 Foundation · WS2 Control-plane · WS3 Spec · WS4 Provisioning · WS5 Migration · WS6 Testing · WS7 SoR/Deploy · WS8 Operate · WS9 Decommission
Depends On | WBS IDs that must complete (or be designed) before this task can proceed.
Risk (Migration sheet) | High = data-loss / availability exposure · Med = recoverable with effort · Low = reversible / read-only.
Core principle | 'AI proposes, human decides.' Anything irreversible, risk-bearing, or policy-binding stays a human gate — even when AI does the drafting and the reversible execution.